## Slide 1: TVO today
Les Entretiens Européens, Brussels 13.10.2022

## Slide 2: Nord Pool market prices, Finnish price area

## Slide 3: OL3 power output during test production phase
12.10.2022

## Slide 4: Olkiluoto 3 milestones
2002
2003
2004
2005
2006
2007
2008
2009
2010
2011
2012
2013
2014
2015
2016
2017
2018
The decision-in-principle by in the Finnish parliament
Contract signing between TVO and the plant supplier
TVO started the infra works and handed the construction site to Areva-Siemens
July, First concrete poured
Installation of the bottom part of containment liner
Reactor building containment liner rises to level +12,5 m
Reactor building dome installed
Manpowerpeak 4500
Pressurizer was brought into the reactor building
Outer dome of the reactor building was completed
Turbine island was connected to the national grid
Cooling water tunnels in use
Reactor pressure vessel closure head installed
Contain-ment pressure tests completed
Safety automation systems arrived in Olkiluoto
Cold functional tests competed
2019
Fuel is in Olkiluoto
Hot functional tests competed
Operators got licenses
2021
Comple-tion of Full Scope Simula-tor testing
Finnish Government granted opera- ting licence
Steam generators in place
Fuel loading
First Criticality
2022
Start of electricity production

## Slide 6
Olkiluoto 3
Fuel Loading 27th March – 1st April 2021

## Slide 7: The connection to grid 12 March 2022, at 12.01 p.m.

## Slide 8
SUPPORT FOR NUCLEAR POWER IN FINLAND
What is your general attitude to nuclear power as an energy source in Finland?
Source: Kantar TNS 2022,
Energiateollisuus ry
Chart: 
| 1983 | 1984 | 1985 | 1986 | 1987 | 1988 | 1989 | 1990 | 1991 | 1992 | 1993 | 1994 | 1995 | 1996 | 1997 | 1998 | 1999 | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022
Negative | 0.38 | 0.51 | 0.39 | 0.32 | 0.44 | 0.44 | 0.37 | 0.39 | 0.34 | 0.35 | 0.41 | 0.43 | 0.35 | 0.39 | 0.35 | 0.32 | 0.32 | 0.34 | 0.26 | 0.3 | 0.32 | 0.28 | 0.25 | 0.2 | 0.19 | 0.17 | 0.17 | 0.21 | 0.23 | 0.26 | 0.26 | 0.24 | 0.25 | 0.25 | 0.23 | 0.22 | 0.15 | 0.16 | 0.16 | 0.11
Positive | 0.24 | 0.17 | 0.3 | 0.35 | 0.22 | 0.25 | 0.26 | 0.26 | 0.29 | 0.29 | 0.26 | 0.29 | 0.34 | 0.35 | 0.33 | 0.35 | 0.38 | 0.41 | 0.44 | 0.39 | 0.35 | 0.45 | 0.46 | 0.5 | 0.46 | 0.47 | 0.48 | 0.47 | 0.42 | 0.42 | 0.41 | 0.41 | 0.43 | 0.39 | 0.41 | 0.41 | 0.49 | 0.49 | 0.49 | 0.6

## Slide 9
NUCLEAR INDUSTRY’S DILEMMA
Solutions are expected from us in the 2020s, but we can offer them in the 2030s
Acceptability is the highest ever, need for new nuclear is clear.
Industry is suffering from country specific regulation, FOAK problem
SMR technology is not yet available.

## Slide 10: Harmonization and use of standard industrial component is the key for future
IAEA, NHSI -project
European SMR Partnership
Nordic KELPO
New, harmonized KELPO-processes
New Nuclear Energy Act + YVL-guidelines in Finland

## Slide 11
We have a solution
for the final disposal
of spent fuel
We have a significant
role in climate change
as a part of the
sustainable nuclear energy
#wehaveasolution
Equipment development
Site investigations
Development of the engineered barriers